## TASKS
TASK LIST
MY TASKS | START DATE | DATE COMPLETED | % COMPLETE | DONE | NOTES | CRITERION
Find a solution to the problem presented and speak to my client | 2022-01-22 | 2022-01-24 | 100% |  | I decided on making a learning app to help organise flashcards for my teacher | A
Start making artifacts for my application | 2022-01-22 | 2022-03-19 | 100% |  | I drew diagrams and wrote algorithms, as my idea developed and I started coding a lot of changes were made to my artifacts. | B
Deciding on what technology to use. | 2022-01-27 | 2022-02-11 | 100% |  | I wanted to use Java, HTML ans CSS to create a web application. | C
Finally deciding on which technology to use | 2022-02-11 | 2022-02-11 | 100% |  | I switched to flutter and Firebase after I saw the demos of my classmates. | C
Make changes to my artifacts, turning them from web based app oriented diagrams to mobile oriented diagrams. | 2022-02-12 | 2022-03-19 | 100% |  | I made appropriate changes to my applications keeping in mind the time constraint, my skill constraint, etc. | B
Speaking to my client and showing them my completed artifacts(at the time) | 2022-02-15 | 2022-02-15 | 100% |  | I further changed my artifacts, keeping in mind my client's feedback.I was now satisfied with my artifacts. | B/A
I try to add a feature to my login page and create a error (I try, but it doesn’t work out very well)I ask my teacher for help | 2022-02-16 | 2022-02-16 | 100% |  | My entire login page is integrated,I have views of all the other screens. | C
Start learning flutter | 2022-02-16 | 2022-01-16 | 100% |  | I started learning flutter, I didn't learn about it in-depth, just what was required for my application. | C
Start coding my login page | 2022-02-17 | 2022-03-18 | 100% |  | I started coding my login page, however I had some issues with integrating it with Firebase. | C
speaking to my client and showing her the login page and registration page | 2022-02-23 | 2022-02-23 | 100% |  | I made appropriate changes to my applications according to my client.I also felt better after seeing my client's positive response. | A
I edit my wireframes, I am struggling a lot with how my app should look (colour, structure, etc) | 2022-03-06 | 2022-03-06 | 100% |  | I learn how to colour texts, add borders to textboxes,layering containers, etc. | C
I add features such as adding flashcards, teacher's view, editing flashcards | 2022-03-11 | 2022-03-11 | 100% |  | I learn the structure that my data is being stored in Firebase | C
I edit my wireframes, and all other components of my project | 2022-03-15 | 2022-03-17 | 100% |  | I add finishing touches and modify my project. | ALL
I realise my class diagram is not in line with my project as I chaanged my technology | 2022-03-16 | 2022-03-17 | 100% |  | I modify my class diagram and use case diagram. | B
I send my client a demo of my project | 2022-03-20 | 2022-03-21 | 100% |  | No notes | A
I record a video of myself showcasing my project | 2022-03-21 | 2022-03-21 | 100% |  | No notes | D
I write down my evaluation of my project | 2022-03-21 | 2022-03-21 | 100% |  | no notes | E
I draw a logo and add it to my app | 2022-03-21 | 2022-03-21 | 100% |  | I was not able add a picture of a flower as per my client's request. | C
I change the design and feel of my app | 2022-03-21 | 2022-03-21 | 100% |  | I make my app look more appealing to kids | C
Convert my work into a ZIP file to submit | 2022-03-21 | 2022-03-21 | 100% |  | No notes | ALL